## Overview
NOTE APP — TEAM 5 ¦ DELIVERY OVERVIEW
Planning horizon | 9 weeks |  | Total backlog hours | 571
Team size | 5 |  | Planning buffer (h) | 149
Hours per member per week | 16 |  | Utilization % | 79.31%
Total capacity (h) | 720 |  | Tasks | 58
Member | Planned Hours | Capacity Hours | Slack Hours |  | Week | Planned Hours | Capacity Hours
M1 | 84 | 144 | 60 |  | 1 | 88 | 80
M2 | 117 | 144 | 27 |  | 2 | 86 | 80
M3 | 120 | 144 | 24 |  | 3 | 86 | 80
M4 | 125 | 144 | 19 |  | 4 | 72 | 80
M5 | 125 | 144 | 19 |  | 5 | 88 | 80
[5 empty] | 6 | 47 | 80
[5 empty] | 7 | 40 | 80
[5 empty] | 8 | 41 | 80
[5 empty] | 9 | 23 | 80
Status note: estimates are provisional. Update Status and Hours before each sprint planning.

## Backlog
Task ID | Week | Owner | Epic | Requirement | Task | Hours | Depends On | Priority | Acceptance | Status
T001 | 1 | M1 | PM | DEC-01..14 | Kickoff và chốt decision log | 10 |  | P0 | Decision statuses có approver | Not Started
T002 | 1 | M1 | ARCH | ADR-001 | Chốt module boundaries và dependency rules | 8 | T001 | P0 | ADR và import gate spec | Not Started
T003 | 1 | M2 | UI | CST-03 | Prototype three-pane và view states | 11 | T001 | P0 | UX flow và demo | Not Started
T004 | 1 | M2 | UI | CST-03 | UI event pump queue main thread POC | 7 | T002 | P0 | No Tk call from worker | Not Started
T005 | 1 | M3 | CORE | FR-01,02 | Domain entities validations và value objects | 12 | T002 | P0 | Unit positive negative | Not Started
T006 | 1 | M3 | CORE | ARCH | Ports DTOs fakes initial contract | 7 | T002 | P0 | No infrastructure imports | Not Started
T007 | 1 | M4 | DATA | CST-04 | Mongo dev compose and schema bootstrap | 10 | T002 | P0 | Local start repeatable | Not Started
T008 | 1 | M4 | DATA | FR-08 | GridFS feasibility spike & limits | 5 | T007 | P0 | 1MiB boundary demonstrated | Not Started
T009 | 1 | M5 | QA | RTM | Test harness lint architecture gate CI | 12 | T002 | P0 | CI runs pytest and ruff | Not Started
T010 | 1 | M5 | QA | NFR-PERF-02 | Deterministic fixture generator 10k notes | 6 | T007 | P1 | Fixture seeded/repeatable | Not Started
T011 | 2 | M1 | PM | SRS | Sign off baseline and UI/API contracts | 7 | T001,T002 | P0 | CR policy and baseline approved | Not Started
T012 | 2 | M2 | UI | FR-01,02 | Editor form and dirty saving saved states | 13 | T003,T006 | P0 | Save actions and UI state demo | Not Started
T013 | 2 | M2 | UI | FR-04,05 | Sidebar category and priority editor | 7 | T012 | P0 | Category selection working | Not Started
T014 | 2 | M3 | CORE | FR-01,02 | CreateNote UpdateNote and version check | 13 | T005,T006 | P0 | Unit tests save and conflict | Not Started
T015 | 2 | M3 | CORE | FR-04,05 | Categories and priority use cases | 7 | T006 | P0 | Validation and uniqueness contract | Not Started
T016 | 2 | M4 | DATA | FR-01,02 | Mongo notes categories repositories | 14 | T007,T006 | P0 | Integration CRUD with Mongo | Not Started
T017 | 2 | M4 | DATA | FR-04 | Schema indexes and migration v2 | 7 | T016 | P0 | Migration tested rollback | Not Started
T018 | 2 | M5 | QA | FR-01..05 | CRUD integration edge scenarios | 12 | T014,T016 | P0 | Core tests pass in CI | Not Started
T019 | 2 | M5 | QA | CST-05 | Windows Ubuntu cross-platform smoke | 6 | T012 | P1 | Platform evidence logged | Not Started
T020 | 3 | M1 | PM | ARCH | Review search semantics & acceptance | 7 | T011 | P0 | DEC-07 confirmed | Not Started
T021 | 3 | M2 | UI | FR-06,07 | Search/filter UI debounce stale response guard | 13 | T012 | P0 | Late response ignored | Not Started
T022 | 3 | M2 | UI | FR-03,13 | Trash view delete restore dialogs | 8 | T012 | P0 | Cancel hard delete safe | Not Started
T023 | 3 | M3 | CORE | FR-06,07,11 | Typed search sort filter use cases | 13 | T014 | P0 | Unit filters and cursor | Not Started
T024 | 3 | M3 | CORE | FR-03,13 | Trash restore hard delete use cases | 8 | T014 | P0 | Explicit state transitions | Not Started
T025 | 3 | M4 | DATA | FR-06,07,11 | Mongo text time range and sort indexes | 12 | T016 | P0 | explain and accurate results | Not Started
T026 | 3 | M4 | DATA | FR-13 | Purge worker scaffold and maintenance state | 7 | T016 | P0 | No TTL orphan hazard | Not Started
T027 | 3 | M5 | QA | FR-06,07,11 | Vietnamese search boundary and race tests | 12 | T023,T025 | P0 | Search semantics evidence | Not Started
T028 | 3 | M5 | QA | FR-03,13 | Trash restore and purge tests | 6 | T024,T026 | P0 | Data integrity scenarios | Not Started
T029 | 4 | M1 | PM | ARCH | Attachment lifecycle ADR and security review | 7 | T020 | P0 | Data cleanup contract approved | Not Started
T030 | 4 | M2 | UI | FR-08 | Image selection thumbnail progress errors | 11 | T012 | P0 | UI does not freeze | Not Started
T031 | 4 | M3 | CORE | FR-08 | Attachment use case validate and replace | 10 | T024 | P0 | Old ref retained until success | Not Started
T032 | 4 | M4 | DATA | FR-08 | Hybrid inline BSON GridFS storage | 15 | T008,T016 | P0 | Size boundaries pass | Not Started
T033 | 4 | M4 | DATA | FR-08 | GridFS compensations orphan reconcile | 10 | T032 | P0 | Fault injection passes | Not Started
T034 | 4 | M5 | QA | FR-08 | Image boundary corruption and interruption tests | 13 | T032 | P0 | No orphan and no crash | Not Started
T035 | 4 | M5 | QA | NFR-PERF-04 | Measure memory and UI event latency | 6 | T030 | P1 | Raw measurements stored | Not Started
T036 | 5 | M1 | PM | SEC | Threat model direct DB / offline + checkpoint | 8 | T029 | P0 | Security review actions tracked | Not Started
T037 | 5 | M2 | UI | FR-09,10 | Reminder UX states and time conversion | 10 | T012 | P0 | Reject past and display UTC local | Not Started
T038 | 5 | M2 | UI | FR-17 | Offline banner and draft recovery modal | 8 | T012 | P0 | No false Saved label | Not Started
T039 | 5 | M3 | CORE | FR-09,10 | Reminder use cases fake clock state machine | 12 | T014 | P0 | Time travel unit tests | Not Started
T040 | 5 | M3 | CORE | FR-17 | RecoverDraft idempotency conflict flows | 9 | T014 | P0 | No overwrite on version mismatch | Not Started
T041 | 5 | M4 | DATA | FR-09,10 | Reminder poller OS notification gateway | 12 | T026,T039 | P0 | Best effort attempt documented | Not Started
T042 | 5 | M4 | DATA | FR-17 | AESGCM local draft keystore backoff | 14 | T016,T040 | P0 | Ciphertext only persists | Not Started
T043 | 5 | M5 | QA | FR-09,10,17 | Offline restart missed reminder fault tests | 15 | T041,T042 | P0 | System scenarios green | Not Started
T044 | 6 | M1 | PM | PM | Release scope lock and risk closure | 7 | T036 | P0 | No open unknown blocker | Not Started
T045 | 6 | M2 | UI | CST-03 | Fix integration UX async shutdown and badges | 12 | T038 | P0 | No UI cross-thread update | Not Started
T046 | 6 | M3 | CORE | CORE | End to end hardening and error mapping | 13 | T040 | P0 | Complete use case suite | Not Started
T047 | 8 | M1 | DATA | NFR-REL | Backup restore rehearsal + retries | 13 | T042 | P0 | Restored fixture matches | Not Started
T048 | 6 | M5 | QA | RTM | Full regression suite and bug triage | 15 | T043,T034 | P0 | No P0/P1 blocker | Not Started
T049 | 9 | M1 | PM | PM | UAT decision sign off release notes | 10 | T044,T048,T047 | P0 | Approval and limitations written | Not Started
T050 | 8 | M2 | UI | CST-02 | Accessibility polish, user guide screenshots | 9 | T045 | P1 | User journey documented | Not Started
T051 | 8 | M3 | CORE | DOC | Contract docs and architecture handoff | 8 | T046 | P1 | Interfaces documented | Not Started
T052 | 8 | M4 | OPS | CST-05 | Build package and install instructions | 11 | T047 | P0 | Artifact reproducible | Not Started
T053 | 9 | M5 | QA | NFR | Benchmark report and final platform matrix | 13 | T048,T052 | P0 | No unverified NFR claimed passed | Not Started
T054 | 7 | M2 | UI | CST-03 | RC UI smoke fixes and usability polish | 8 | T045 | P0 | No blocking UI issue | Not Started
T055 | 7 | M3 | CORE | FR-01..11 | Resolve E2E integration defects | 8 | T046,T048 | P0 | All critical use cases pass | Not Started
T056 | 7 | M4 | DATA | CST-04 | GridFS and purge integrity audit | 8 | T033,T048 | P0 | No orphan known at release checkpoint | Not Started
T057 | 7 | M5 | QA | RTM | Release candidate smoke and defect audit | 9 | T048 | P0 | RC report available | Not Started
T058 | 7 | M1 | PM | PM | UAT dry run and acceptance evidence check | 7 | T044,T048 | P0 | Demo ready | Not Started